## Summary
PROGRESS CLAIM
Claimant (company name and UEN)
Respondent
Project (title and site)
Contract / subcontract reference
| Claim number | PC 01
Claim period (work up to)
Date of claim
This is a payment claim made under the Building and Construction Industry Security of Payment Act 2004.
(Optional statement. Delete this line if you do not want to use it.)
Inputs
Contract sum (S$)
| Retention rate | 5%
Retention limit (S$, blank = none)
| Materials on site (S$, if the contract allows) | 0
| Previous certified amounts, excl. GST (S$) | 0
| GST rate (blank if not GST-registered) | 9%
Line | Item | Amount (S$)
1 | Contract sum
2 | Contract work done to date
3 | Variations done to date
4 | Materials on site
5 | Gross value to date (2 + 3 + 4)
6 | Less retention (rate × line 5, up to the limit)
7 | Net value to date (5 − 6)
8 | Less previous certified amounts
9 | Amount claimed this period (7 − 8)
10 | GST
11 | Total amount claimed this period (9 + 10)
Yellow cells are inputs. Everything else is calculated.
Retention, payment terms and GST treatment come from your contract; check them before you send the claim.
This template is general information, not legal advice. Check the current SOP Act and take legal advice on disputes.
Template by CCorex (ccorex.com). DeepTrack prepares numbered progress claims with retention, 9% GST and a PDF certificate.

## Valuation
Valuation sheet (contract work)
Item | Description | Contract amount (S$) | % to date | Value to date (S$) | Previously claimed (S$) | This period (S$) | Remarks
Total
Tip: enter % complete (e.g. 40%), or overwrite column E with quantity × rate.

## Variations
Variations
VO ref | Description | VO amount (S$) | % to date | Value to date (S$) | Previously claimed (S$) | This period (S$) | Status | Remarks
Total
Tip: enter % complete (e.g. 40%), or overwrite column E with quantity × rate.