## Cost report
MONTHLY PROJECT COST REPORT
Project
Report month
Prepared by
Currency | SGD, before GST
Revenue
Contract value
Approved variations
Expected variations (not yet agreed)
Claimed to date
Certified to date
Forecast final revenue
Cost by cost code
Cost code | Budget | Committed (POs and subcontracts) | Actual to date | Cost to complete (PM estimate) | Forecast final cost | Variance (budget less forecast) | Variance % | Reason and action
Materials
Subcontract labour
Direct labour
Equipment and testing
Preliminaries
Overhead
Total
Margin
Budget margin (contract value + approved variations − budget)
Forecast margin (forecast final revenue − forecast final cost)
Forecast margin %
Committed but not yet invoiced (check cost to complete covers it)
Yellow cells are inputs. Forecast final cost = actual to date + cost to complete. Negative variance (red) means over budget.
Cost to complete is the PM's estimate of what is still needed, including commitments not yet invoiced. Do not set it to budget minus actual.
Template by CCorex (ccorex.com). General information, not accounting advice.

## Monthly trend
Forecast final cost and margin by month
Month | Budget | Actual to date | Forecast final cost | Forecast final revenue | Forecast margin | Forecast margin % | Comment
Copy the totals from the "Cost report" sheet here at each month-end, so the trend is kept.

## Notes
How to use this template
1. Use the same cost codes as your approved budget, so budget and actuals line up row by row.
2. Close the month first: post matched invoices and allocate labour and overhead, so "Actual to date" is complete.
3. "Committed" is every approved PO and subcontract value, invoiced or not. Remove cancelled orders.
4. Ask the PM for "Cost to complete" code by code, in figures, with a reason for any change from last month.
5. Explain every variance above your threshold in the "Reason and action" column.
6. Fill the revenue block, including approved variations and, separately, variations you expect to be agreed.
7. Copy the month's totals to the "Monthly trend" sheet and keep each month's report.
Figures are before GST. This template is general information, not accounting advice.
Guide: ccorex.com/resources/construction-cost-report-template